## Method Of Procedure
Method Of Procedure
CC#XXXXX				SERVICE/APPLICATION/SYSTEM IMPACT	CONTACT POINT (Change Owner)			Information to rationalize change
<TO DO Detail>				<SYSTEM NAME>	< TBD >
Communication Plan(Annoucement) / Documentation Handover
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
1
2
3
4

Backup Plan
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
1				No backup required because / - This deployment not involve changing/modifying existing data in the database / - we will use rollback step to revert system back to before change in case of no-go decision
2
3
4

IMPLEMENTATION STEPS
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
1. DBA task				1. Create database user ทั้งบน on premise และ on cloud
1.1	11 Jan 2017	0.833333333333333	0.836805555555556	1. Log-in xzxxxx by root		cheewaphat (SA)	866954585
1.2	11 Jan 2017	0.836805555555556	0.840277777777778	2. Create directory /mnt/CM / # mkdir /mnt/CM	# ls -l /mnt/CM / Total 0	cheewaphat (SA)	866954585
1.3	11 Jan 2017	0.840277777777778	0.84375	3. Add the following line in /etc/fstab / 10.50.72.108:/LandingZone/incoming/CM /mnt/CM nfs	# cat /etc/fstab / Found the line /LandingZone/incoming/CM	cheewaphat (SA)	866954585
1.4	11 Jan 2017	0.84375	0.847222222222222	4. Mount NFS filesystem / # mount /mnt/CM	# df -h /mnt/CM / New filesystem should be found	cheewaphat (SA)	866954585

2. App team task to create table				CREATE USER "ORACAPT" PROFILE "DEFAULT"
1.5	11 Jan 2017	0.847222222222222	0.864583333333333	Run script from tab “script create table” / - CREATE DATABASE / - CREATE TABLE	DATABASE CM created / Total 16 tables created	CIS (Thaveewat)	0891556592
3. Sanity Test				- cd /Informatica/PowerExchange/install	Untar
3.1	11 Jan 2017	0.864583333333333	0.875		Can select data from tables / No error message returned	TBD	TBD

RollBack Plan (No Go from Check point# 1, 2 ,3)					(refer to PWX install log.TXT in CC)
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)		Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
4. Rollback Sanity Test. If failed step 3.1
4.1	11 Jan 2017	0.864583333333333	0.868055555555556	Unmount NFS / # unmount /mnt/CM	df -h /mnt/CM / Not found filesystem	DBA (Pornchai)
4.2	11 Jan 2017	0.868055555555556	0.871527777777778	Remove the following from /etc/fstab	# cat /etc/fstab / Not found this line	DBA (Pornchai)
4.3	11 Jan 2017	0.871527777777778	0.875	Remove directory / # rmdir /mnt/CM	# ls -l /mnt/CM / No such file or directory	DBA (Pornchai)
4.4	11 Jan 2017	0.875	0.881944444444444	DROP TABLE created in step 2.1	tables dropped	CIS (Thaveewat)

Post Implementation Monitoring
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No

## Mount NFS
Mounting NFS File System '/mnt/cm'

1. Log-in xxxxx

2. Create directory '/mnt/cm'

3. Add the following line in /etc/fstab

4. Mount the NFS file system

5. Verify new NFS filesystem. The new filesystem /mnt/cm should be found

## script create table
Task	Table	Script On Impala

## Rollback Mount NFS
Rollback Mounting NFS File System '/mnt/cm'
1. Log-in xxxxx

2. Unmount the NFS file system

3. Remove the new line from /etc/fstab

4. Remove directory /mnt/cm