## Method_Of_Procedure
Method Of Procedure
CC#C00034447				SERVICE/APPLICATION/SYSTEM IMPACT	CONTACT POINT (Change Owner)			Information to rationalize change
switch interface OSB to kafka consumer				ODS	Cheewaphat Loyjew(086 695 4585)			Get data form kafka server to TGW on Data wherehouse
Communication Plan(Annoucement) / Documentation Handover
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
1	2018/02/27	23:00	23:05	Off OSB Service		Proudpalin Vorayabenjapisuth	086-522-3347
2	2018/02/27	23:00	23:05	On Kafka consumer		Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
3	2018/02/27	23:05	23:10	On Kafka temp consumer		Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
4	2018/03/06	9:00	9:00	Merge data from temp		Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
5	2018/02/27	23:30	23:35	Stop Informatica job workflow WF_CCP_TGW		Natthawat (OPS), / Cheewaphat Loyjew (CIS)	064-702-1269 / 086-695-4585

Backup Plan
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
1				No backup required because / - This deployment not involve changing/modifying data in the database / - we will use rollback step to revert system back to before change in case of no-go decision
2
3
4

IMPLEMENTATION STEPS
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
Operation Task
1. Stop TGW Server
1.1	2018/02/27	23:00:00 PM	23:05:00 PM	Stop OSB / Please follow TAB > Stop OSB	Stop done.	Proudpalin Vorayabenjapisuth	086-522-3347

2. Start Kafka consumer
2.1	2018/02/27	23:00:00 PM	23:05:00 PM	Login hdpidbpr1 ( 172.19.160.28 ) / > ssh lcisetl3@hdpidbpr1	Login complete	Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
2.2	2018/02/27	23:05:00 PM	23:10:00 PM	Enabled crontab kafka consumer		Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
2.2	2018/02/27	23:10:00 PM	23:15:00 PM	Check service processing / > ~/PROJECT_TGW_SUBSCRIBE/service.bash status	แสดง config.ini ของ topic ที่ subscribe	Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
3. Start Kafka Temp consumer
3.1	2018/02/27	23:10:00 PM	23:15:00 PM	Login hdpmnappr2 / > ssh hdppr1_cisetl1@hdpmnappr2	Login complete	Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
3.2	2018/02/27	23:15:00 PM	23:20:00 PM	Run service kafka temp consumer / > /home/hdppr1_cisetl1/PROJECT_TGW_SUBSCRIBE_TMP/service.bash start / > /home/hdppr1_cisetl1/PROJECT_TGW_SUBSCRIBE_TMP/service.bash repair all	มี data เข้า temp table @ODSDEV2 ( NRTSTGAPPO.TGW_AA , NRTSTGAPPO.TGW_CCP ) / – TGW_CCP / select event_type,count( *) ,min(event_begintime),min(ods_ppn_tm),max(ods_ppn_tm) / from TGW_ccp / group by event_type / order by 3 desc / -- TGW_AA / select event_type,count( *) ,min(event_begintime),min(ods_ppn_tm),max(ods_ppn_tm) / from TGW_AA / group by event_type / order by 3 desc	Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
3.2	2018/02/27	23:20:00 PM	23:25:00 PM	Check service processing / > /home/hdppr1_cisetl1/PROJECT_TGW_SUBSCRIBE_TMP/service.bash status	แสดง config.ini ของ topic ที่ subscribe

4. Merge Data from temp to production
4.1	2018/02/28	09:00:00 PM	09:00:00 PM	Login hdpmnappr2 / > ssh hdppr1_cisetl1@hdpmnappr2		Woraon Pratoomsuwan / Cheewaphat Loyjew	086-516-1425
4.2	2018/02/28	09:00:00 PM	09:35:00 PM	Run script for merge / > /prod1/cisetl_apps3/lcisetl3/PROJECT_TGW_SUBSCRIBE_TMP/merge_temp2prod.bash / *Remark run 7 day	Run script has succeeded มี data เข้าใน table / -- TGW_AA / select event_type,count( *) ,min(event_begintime),min(ods_ppn_tm),max(ods_ppn_tm) / from TGW_AA / where ods_upd_by = 'ODSMIGRATION' / group by event_type / order by 3 desc / -- TGW_CCP / select event_type,count( *) ,min(event_begintime),min(ods_ppn_tm),max(ods_ppn_tm) / from TGW_CCP / where ods_upd_by = 'ODSMIGRATION' / group by event_type / order by 3 desc	Woraon Pratoomsuwan / Cheewaphat Loyjew
4.3	2018/03/06	09:35:00 PM	09:45:00 PM	Stop Service / > /prod1/cisetl_apps3/lcisetl3/PROJECT_TGW_SUBSCRIBE_TMP/service.bash stop	No Service temp is running
5. Stop workflow WF_CCP_TGW
	2018/03/06	10:00:00 PM	10:10:00 PM	Stop workflow TAB > Start workflow		Natthawat (OPS), / Cheewaphat Loyjew (CIS)	064-702-1269 / 086-695-4585

RollBack Plan (No Go from Check point# 1, 2 ,3)
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
5. Rollback Sanity Test. If failed step 1
5.1	2018/02/27	23:30:00 PM	23:45:00 PM	#checkpoint 1 / remove crontab	crontab removed	Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
5.2	2018/02/27	23:35:00 PM	23:45:00 PM	Start TGW Server / Please follow TAB > Start TGW Servrer	Start TGW Server has started	Proudpalin Vorayabenjapisuth	086-522-3347

6. Rollback Sanity Test. If failed step 2
	2018/02/27	23:30:00 PM	23:31:00 PM	#checkpoint 1 / remove crontab	crontab removed	Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
	2018/02/27	23:31:00 PM	23:35:00 PM	#checkpoint 2 / Remove PROJECT_TGW_SUBSCRIBE / > rm -rf ~/PROJECT_TGW_SUBSCRIBE/	application folder removed	Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
	2018/02/27	23:31:00 PM	23:35:00 PM	Start TGW Server / Please follow TAB > Start TGW Servrer	Start TGW Server has started	Proudpalin Vorayabenjapisuth	086-522-3347

7. Rollback Sanity Test. If failed step 3
	2018/02/27	23:40:00 PM	23:41:00 PM	#checkpoint 1 / remove crontab	crontab removed	Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
	2018/02/27	23:41:00 PM	23:45:00 PM	#checkpoint 2 / Remove PROJECT_TGW_SUBSCRIBE_TMP / > rm -rf ~/PROJECT_TGW_SUBSCRIBE_TMP/	application folder removed	Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
	2018/02/27	23:45:00 PM	23:45:00 PM	Start TGW Server / Please follow TAB > Start TGW Servrer	Start TGW Server has started	Proudpalin Vorayabenjapisuth	086-522-3347

8. Rollback Sanity Test. If failed step 4
	2018/03/06	09:30:00 AM	09:40:00 PM	Remove data on production	DELETE FROM NRTSTGAPPO.TGW_CCP / WHERE ods_ppn_by IN ('ODSMIGRATION')	Woraon Pratoomsuwan (OPS), / Cheewaphat Loyjew (CIS)	086-516-1425 / 086-695-4585
8. Rollback Sanity Test. If failed step 5
	2018/03/06	10:30:00 AM	10:40:00 PM	Start WF_CCP_TGW ตาม Tab Start Workflow

Post Implementation Monitoring
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
1	2018/02/28 – 2018/03/06	09:00:00 AM	18:00:00 PM	เช็คข้อมูลเข้า target table ,temp table ที่ ODSPRD2,ODSDEV2 (TGW_LOG, TGW_CCP) ว่ามีข้อมูลไหลเข้า โดยให้ monitor เป็นเวลาประมาณ 7	มี data เข้า temp table และ target table / -- TGW_AA / select event_type,count( *) ,min(event_begintime),min(ods_ppn_tm),max(ods_ppn_tm) / from TGW_AA / where ods_ppn_tm >= to_date('2018-02-27','RRRR-MM-DD') / group by event_type / order by 3 desc / -- TGW_CCP / select event_type,count( *) ,min(event_begintime),min(ods_ppn_tm),max(ods_ppn_tm) / from TGW_CCP / where ods_ppn_tm >= to_date('2018-02-27','RRRR-MM-DD') / group by event_type / order by 3 desc	Cheewaphat Loyjew (CIS)	086-695-4585
2

## > Stop  OSB
SCB Site
http://10.7.69.205:7001/console/login/LoginForm.jsp
http://10.7.69.205:7101/console/login/LoginForm.jsp

TST Site
http://10.7.209.136:7001/console/login/LoginForm.jsp
http://10.7.209.136:7101/console/login/LoginForm.jsp

## > Rollback - Start  OSB
SCB Site
http://10.7.69.205:7001/console/login/LoginForm.jsp
http://10.7.69.205:7101/console/login/LoginForm.jsp

TST Site
http://10.7.209.136:7001/console/login/LoginForm.jsp
http://10.7.209.136:7101/console/login/LoginForm.jsp

## Stop Workflow
Figure 1

Figure 2

Figure 3

## Start Workflow
Figure 1

Figure 2

Figure 3

Figure 4