## Method_Of_Procedure
Method Of Procedure
CC#XXXXX				SERVICE/APPLICATION/SYSTEM IMPACT	CONTACT POINT (Change Owner)			Information to rationalize change
[Telesale] Install CDC data replication from source system to ODS				PDS	Pasit Boonyakiat (0863814440)			Need source data to be replicated to ODS to support report requirement of Mahanakorn and Telesale project
Communication Plan(Annoucement) / Documentation Handover
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
1
2
3
4

Backup Plan
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
1				No backup required because / - This deployment not involve changing/modifying data in the database / - we will use rollback step to revert system back to before change in case of no-go decision
2
3
4

IMPLEMENTATION STEPS
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
1. Preparation before implementation time
1.1	1 Feb 2017	09:00:00 AM	05:00:00 PM	Create user on PDS database server (IP : 172.30.181.180) / - OS user : pwxadmin / - Database user : oracapt / UA#XXXXXXX	User pwxadmin created and owner of directory / User ORACAPT created in database	DBA

2. Installing Informatica Agent
2.1	1 Feb 2017	11:05:00 PM	11:15:00 PM	SERVER IP : 172.30.181.180 / 1. Config "pwxadmin" user environment (.bash_profile)		DBA
2.2	1 Feb 2017	11:15:00 PM	11:20:00 PM	SERVER IP : 172.30.181.180 / 1. Create directory on QRUN database server / mkdir /Informatica/PowerExchange/install / mkdir /Informatica/PowerExchange/PWX / mkdir /Informatica/PowerExchange/PWX/scripts / mkdir /Informatica/PowerExchange/PWX/logs / mkdir /Informatica/PowerExchange/PWX/maps / mkdir /Informatica/PowerExchange/PWX/maps/capture / mkdir /Informatica/PowerExchange/PWX/maps/xtramaps / All directory own by pwxadmin		DBA
2.3	1 Feb 2017	11:20:00 PM	11:30:00 PM	SERVER IP : 172.30.181.180 / 1. sFTP software installer to PDS database server / - /Informatica/PowerExchange/installl/pwx951_04_linux_em64t.tar / 2. untar / - cd /Informatica/PowerExchange/install / - tar -xvf pwx951_04_linux_em64t.tar / 3. install software to destination path / - cd /Informatica/PowerExchange/install / - ./install.sh / - Installation Destination : /Informatica/PowerExchange/PWX	1. file size is below: / 2. untar file is below: / 3. Install complete	DBA
2.4	1 Feb 2017	11:30:00 PM	11:35:00 PM	SERVER IP : 172.30.181.180 / FTP file to PDS server / PDS_dbmover.cfg to / - /Informatica/PowerExchange/PWX/dbmover.cfg / PDS_pwxorad.cfg to / - /Informatica/PowerExchange/PWX/pwxorad.cfg		DBA
3. Enable Supplemental Log
3.1	2 Feb 2017	12:00:00 AM	12:05:00 AM	SERVER IP : 172.30.181.180 / Run command on server: / - Refer to attached file grant_oracapt.sql	Result add supplement log / Result grant select
3.2	2 Feb 2017	12:05:00 AM	12:45:00 AM	Register CDC by using power exchange navigator / 1. Config dbmover.cfg for PowerExchange navigator below: / - Goto Path C:\Informatica\PowerExchange9.5.1 / - Add node / NODE=(PDSPRD,TCPIP,172.30.181.180,2480,262144,262144,262144,262144) / 2. Add Capture Registration / - Refer to "PowerExchange Navigator" and "Capture Registration" sheets	All tables in "Capture Registration" sheet are registered in PowerExchange
3.3	2 Feb 2017	12:45:00 AM	01:00:00 AM	SERVER IP : 172.30.181.180 / Run command on PDS database / - Use alter scripts generated by Step 3.1	all tables are altered	DBA

4. Start Listener
4.1	2 Feb 2017	01:00:00 AM	01:30:00 AM	SERVER IP : 172.30.181.180 run command to start listener services in backgroud mode on PDS database server / $ nohup dtllst node1 &	$ ps -ef | grep dtllst should display process	DBA
5. Sanity Test. CHECKPOINT #1
5.1	2 Feb 2017	01:30:00 AM	01:45:00 AM	SERVER IP : 172.19.195.91 (Power Center DEV) / 1. Check PWX condense file created on PowerCenter Server in path below: / /Informatica/PowerExchange/PDS/condense / 2. Check PWX logger log indicating changed records / tail -f /Informatica/PowerExchange/PDS/logs/detail.log	1. There are files in path / 2.	Pasit_Boo	0863814440

RollBack Plan (No Go from Check point# 1, 2 ,3)
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
6. Rollback Sanity Test. If failed step 5.1
6.1	28/12/2016	01:45:00 AM	01:55:00 AM	Kill agent process / $ ps -ef | grep dtllst / $ kill -9 xxxxx	No agent process should run / $ps -ef | grep dtllst / Should not return any process ID	DBA
6.2	28/12/2016	01:55:00 AM	02:05:00 AM	Delete all software in directory	$ ls -l /u01/Informatica/PowerExchange / No such file or directory / $ ls -l /Informatica/PowerExchange / No such file or directory	DBA
6.3	28/12/2016	02:05:00 AM	02:15:00 AM	Remove supplemental log / ALTER DATABASE DROP SUPPLEMENTAL LOG DATA	SELECT SUPPLEMENTAL_LOG_DATA_MIN, / SUPPLEMENTAL_LOG_DATA_PK, / SUPPLEMENTAL_LOG_DATA_UI / FROM V$DATABASE; / Return NO, NO, NO	DBA

Post Implementation Monitoring
No	Date	Planed Time		Procedure / (ขั้นตอนการดำเนินการ)	Result	Responsible / (ผู้รับผิดชอบ)	Mobile no. / ( เบอร์โทรติดต่อ)	Completed		Remark
		Start Time	End Time		status			Yes	No
1	28/12/2016 – 3/1/2017			Monitoring CPU, Memory and I/O on QRUN database servers for 1 week	Agent should not have high impact on app operation	DBA
2
3

## PowerExchange_Navigator
1. Open PowerExchange Navigator

2. Right Click on Registration Group -> Add Registration Groups

3. Input information then click Next

4. Input name (8 character), Schema and Table

5. Double click on table and check "Select all and notify changes" and click Next

6. Config Type below:
Type: Synchronous
Status: Active
Condense: Part
Supplement Log Group Name: [suggest to be same as capture registration name]

7. Click Finish and save alter scripts sql into path

8. capture registration show in resource explorer

## Capture_Registration
SOURCE SCHEMA	SOURCE TABLE	CAPTURE NAME	SUPPLEMENT LOG GROUP NAME	TARGET TABLE
GENOUTBOUND1	TBL_TSM_CALLLIST	TBTSCALL	TBTSCALL	PDS_TBL_TSM_CALLLIST